## Annex B Action Table
THIS IS A LIVING DOCUMENT WHICH WILL BE REVIEWED AND UPDATED THROUGHOUT THE LIFE OF THE LSIP. IT IS OUR INTENTION TO REVIEW AND ESTABLISH BASELINES DURING THE FIRST THREE MONTHS OF YEAR 1
Change Action/Theme | Action | Priority | Lead | Supporting Partners | LSIP Outcomes | Outputs (Year 1) | Outcomes (Years 1-3) | Impact (Years 1-3) | Metrics | Baseline/Targets | Data Sources | Milestones
[12 empty] | Year 1 | Year 2 | Year 3
Cross Cutting Actions
4.1 Increase workforce supply in priority sectors | 4.1.1.1 Grow apprenticeship volumes, through increasing the number of apprenticeship opportunities offered by employers and by increasing the take-up of these opportunities by learners:
| Develop and implement an enhanced or replacement Apprenticeship Hub | H | SHC or WBLPF | CoC, other ERBs | O1, O2, O3 | Hub operational; employers registered and actively using the service | Increased employer use of apprenticeships; Increased learner take-up | Reduction in vacancy rates in priority occupations | Apprenticeship starts and completions by level/sector; number of employers engaged; vacancy levels (SOC-aligned where possible) | Baseline established year 1 (DfE 2025 data); target +15-20% apprenticeship starts by Year 3 | DfE data; provider ILR; employer engagement records | Hub established; baseline set | Increased uptake and employer engagement | Demonstrable reduction in vacancies
| Pilot apprenticeship and training adviser support for employers | H | CoC | SHC, WBLPF, other ERBs | O1, O2, O3 | Pilot launched; employers receiving advice | Increased employer understanding; increased apprenticeship uptake | Sustained increase in apprenticeship participation | Number of employers supported; apprenticeship starts; employer feedback (measured satisfaction score) |  | DfE data; provider ILR; employer engagement records | Pilot delivery; baseline set | Scale services | Embedded service with measurable impact
| Develop and share awareness and understanding communications and resources | H | CCA/CH | CoC, other ERBs, WBLPF, SHC | O1, O3 | Activity and resources launched and delivered | Increased employer understanding; increased apprenticeship uptake | Sustained increase in apprenticeship participation | Number of employers engaged; apprenticeship starts; employer feedback (measured awareness and understanding score) |  | DfE data; provider ILR; employer engagement records | Plan and resources established; baseline set | Employer engagement | Participation increase demonstrated
| Consider the opportunities for use of a flexi-jobs agency (working with Team Barrow for construction, RCESAP for manufacturing and clean energy, and consider in relation to land-based) | H | TB/RCESAP | CoC, CESSG, LANSS, WBLPF, SHC | O1, O2, O3 | Review completed; actions identified | Increased employer use of apprenticeships; Increased learner take-up | Reduction in vacancy rates in priority occupations | Apprenticeship starts and completions by level/sector; number of employers engaged; vacancy levels (SOC-aligned where possible); employer feedback (satisfaction score); number of schools engaged |  | DfE data; provider ILR; employer engagement records | Research completed; baseline set | Implementation (subject to results of review) | Participation increase demonstrated
| Support employers to develop their talent pipelines through education outreach including e.g. career events and modern work experience | M | CH | CoC, WBLPF, SHC, other ERBs, Inspira, S4C | O3, O5 | Outreach activities delivered; employers participating | Increased SME employer engagement; improved learner awareness of career pathways | Increased participation in sector-specific pathways | Number of employers engaged; participation in outreach activities; progression into apprenticeships or jobs |  | DfE data; provider ILR; employer engagement records | Activities established; baseline set | Expansion of employer involvement | Measurable increase in progression
| Support actions set out in the Apprenticeships Plan | H | CCA | CoC, other ERBs, WBLPF, SHC, Inspira, CESSG, TB | O1, O2, O3, O5 | Actions agreed and implementation started | Increased employer engagement; increased employer use of apprenticeships; increased learner take-up | Sustained increase in apprenticeship participation; reduction in vacancy rates in priority occupations | Apprenticeship starts and completions by level/sector; number of employers engaged; vacancy levels (SOC-aligned where possible) |  | DfE data; provider ILR; employer engagement records | Activities established; baseline set | Increased delivery and participation; increased employer participation | Participation increase demonstrated
| Undertake a piece of work looking at reasons for reducing Level 3 engagement and identify solutions | M | CCA/CoC | CoC, other ERBs, WBLPF, SHC, Inspira, CESSG, TB | O1, O2, O4 | Review completed; actions identified | Changes to provision and engagement strategies | Increased participation in Level 3 provision | Participation in Level 3 provision; number of curriculum adjustments; learner progression rates |  | DfE data; provider ILR; employer engagement records | Research completed; baseline set | Implementation of changes | Participation increase demonstrated
| Utilise the Future Skills Questionnaire (completed by secondary school pupils) and undertake a piece of work gathering and reviewing the views of young people in work and training, using the two to help plan meaningful employer outreach activity and inform provision | M | CoC/CH | other ERBs, WBLPF | O1, O4, O5 | Data collected and analysed; insight report produced | Improved alignment of provision to learner needs; more targeted outreach | Increased participation and improved progression outcomes | Number of young people participating in survey; curriculum/delivery changes informed by insights; learner participation rates |  | DfE data; provider ILR; survey engagement records | Data gathered; baseline set | Insights applied to delivery | Improved participation and outcomes
| Roll out the Cumbria Talent Force utilising relatable role models and challenging stereotypical thinking | M | CH | CoC, other ERBs, WBLPF, S4C | O1, O2, O5 | Talent Force resources expanded; promotion of Talent Force | Increased learner take-up of opportunities | Increased participation in sector-specific pathways | Number of young people participating in Talent Force; number of schools and colleges engaged with Talent Force; employer, provider and learner feedback including measured satisfaction; participation in FE, ASF, Bootcamps and HE |  | Learner feedback records; employer feedback records; DfE data; provider ILR; programme monitoring records | Expansion an promotion of Talent Force resources; baseline set | Increased engagement with Talent Force | Improved understanding of opportunities and pathways; improved participation
| To ensure young people have the essential skills required by employers continue to work with employers and educators to roll out the Essential Skills Programme providing a consistent use of language and approach to developing the 8 skills through outreach activities, extra-curricular activities and workplace experiences | H | CH | CoC, other ERBs, WBLPF | O1, O2, O3 O4 | Roll out of Essential Skills Programme | Improved Essential Skills among young people | Enhanced employability of young people; reduced inactivity among young people | Employer feedback (measured satisfaction score); number of schools/colleges using the programme |  | Employer feedback records (survey); Future Skills Questionnaire responses | Programme roll out; baseline set | Increased delivery and participation with provision adjusted; increased employer engagement | Clear alignment between provision and employer needs; improved employer feedback on essential skills
4.1.1.2 To fill current and emerging needs, while at the same time supporting inclusion and opportunity, there is a need for a range of activities to support more people into the active workforce, in particular those with barriers. These include:
| Continue and grow the ECITB work ready pathway model and expand this approach into other sectors | H | ECITB & others as appropriate | ECITB, CITB, DWP/JCP, CESSG, TB | O1, O5 | Programmes launched /expanded; learners enrolled | Increased participation of unemployed individuals; improved progression into work or training | Reduced inactivity among local residents | Participation numbers; progression into employment; NEET number and participation rates; number of sectors using; number of cohorts run | Baseline established year 1 (2025 ONS data); target to reduce inactivity by 10% by year 3 | DfE data; provider ILR; employer survey records, Jobcentre Plus data; programme monitoring data | Programme roll out; baseline set | Increased participation | Sustained programme outcomes
| Consideration of how we can use ASF and increasing flexibility to get more unemployed local people into L2 training, work & progression | H | CCA | WBLPF, ECITB, CITB, DWP/JCP, CESSG, TB | O1, O2, O5, O6 | Review undertaken and actions identified | Changes to provision; improved alignment to learner and employer needs | Reduced inactivity among local residents; increased participation and progression among unemployed people | Participation in ASF; progression into employment; NEET numbers and participation rates; employment and progression | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | DfE data; provider ILR; employer survey records, Jobcentre Plus data | Review completed; baseline set | Implementation of changes | Improved participation and outcomes
| Development a Good Work Charter (incorporating Disability Confident, Care Leavers Covenant, Armed Forces Covenant, etc) and encourage and support implementation of this by businesses, including through resources and advice | M | CSP | CSP members | O3, O5 | Charter developed; employers signed up | Increased inclusive employment practices | Increased employment participation among disadvantaged groups | Number of employers signed up; number of inclusive employment initiatives implemented; employment outcomes for target groups | Baseline no Charter currently in existence; target Charter in place year 1 and to engage at least 50 employers in the Charter by year 3 | Employer feedback records (surveys), CSP/JCP/other scheme take-up records; programme monitoring data | Charter launched; baselines set | Increased adoption | Measurable employment improvements
| Encourage and support employment of people from wider groups such as people with disabilities/long term health conditions, care leavers/experienced, prisoners on ROTL, ex-offenders, service leavers/veterans, etc. This includes promoting the benefits and opportunities to businesses and engaging and working with prisons, the Work & Health Board (Get Cumbria Working Plan), Connect to Work/Inspira, Armed Forces, etc. | H | CoC | Other ERBs, CSP, W&H Board, Inspira, JCP/DWP, CCA Councils, Armed Forces | O1, O2, O3, O5 | Plan developed; implementation started; employers engaged | Increased inclusive employment practices | Increased employment participation among disadvantaged groups | Number of employers signed up; number of inclusive employment initiatives implemented; employment outcomes for target groups; NEET numbers and participation rates | Baseline established year 1 (scheme records); target to increase employer engagement in these initiatives by 25% by year 3 | Employer feedback records (surveys), CSP/JCP/other scheme take-up records; programme monitoring data | Plan completed and implementation started; baselines established; initial participation and engagement | Broader employer engagement and participation | Measurable employer sign ups and participation; measurable employment improvements
| Consider how we best work with Jobs Plans and agree appropriate actions | H | CoC | Other ERBs, W&HB, Inspira, Councils, CCA, WBLPF, JCP/DWP | O1, O2, O4, O5 | Opportunities reviewed and actions agreed; implementation started | Changes to provision and engagement strategies | Increased employment rates in particular among those with barriers | Number of employers engaged; employment and progression | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Employer feedback records (surveys), CSP/JCP/other scheme take-up records; programme monitoring data | Actions agreed; implementation started; baselines established | Broader employer engagement and participation | Measurable employment improvements
| Align LSIP activity with support for disadvantaged residents offered by Jobcentre Plus whose offer provides tailored support for groups such as young people, disabled individuals, those with health conditions and carers, as well as people with complex barriers - this includes personalised support, the Youth Guarantee, work experience, Sector-Based Work Academy Programmes (SWAPs), in-work support, Access to Work, and other pre-employment and in-work support | H | CoC | Other ERBs, W&HB, Inspira, Councils, CCA, WBLPF, JCP/DWP | O1, O5 | Joint working arrangements in place; employers engaged with JCP support | Increased participation in JCP-supported pathways; improved engagement for disadvantaged groups | Increased employment rates among those with barriers | Participation in JCP programmes; progression into employment; employer engagement levels | Baseline established year 1 (JCP records); target to increase employer engagement in these initiatives by 15-20% by year 3 | Employer feedback records (surveys), CSP/JCP/other scheme take-up records; programme monitoring data | Alignment established | Increased referrals and participation | Improved employment outcomes
| Undertake a piece of work on how the county and businesses can best engage with targeted universities active within and beyond Cumbria to encourage graduates to come to Cumbria to work and move more graduates into graduate jobs | M | CoC | Steering Group, ERB group, universities | O1, O2, O3 | Review undertaken and actions identified | Changes to activities and engagement strategies; programmes implemented | Increased employment of graduates in graduate jobs; more graduates staying in or moving to/back to Cumbria to work | Graduate employment numbers; number of employers engaged; vacancy levels; employer feedback | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Employer surveys; programme monitoring data | Review completed; baseline set | Implementation of changes | Measurable employment improvements
| 4.1.1.3 ASF & Bootcamps - to support more effective pathways and skills development we will use the ASF flexibility which will come with the Combined Authority to ensure Bootcamps offer an effective pathway at Level 2, for example by, reducing the number hours and considering a modular approach, as well as increasing their attractiveness to employers as a tool for upskilling of existing staff. We will also work together to ensure ASF funding is targeted at the skills areas most needed (as well as a direct impact this will also support progress into apprenticeships) | H | CCA | CoC, WBLPF, other ERBs, Councils | O1, O2, O3, O4, O6 | Revised provision model; new or adapted courses implemented | Increased learner take-up; improved employer satisfaction | Better alignment between provision and labour market demand | Participation in Bootcamps/ASF; employer satisfaction; progression rates; employment and participation | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Employer surveys; programme monitoring data | Provision updated | Increased uptake | Measurable alignment with employer demand
| 4.1.1.4 There are a range of identified needs in higher level skills which would have a positive impact on our workforce challenges, not least through helping to keep/attract younger people - this is the across priority sectors, with specifics highlighted in the various sectors below | H | WBLPF | CoC, other ERBs, UoC, NCFN, TB, CESSG | O1, O2, O4 | Provision developed /expanded | Increased learner take-up; improved employer satisfaction; improved alignment to employer needs | Better alignment between provision and labour market demand; reduced vacancy levels in priority occupations (SOC aligned where possible) | Participation in HE provision; graduate and young people employment numbers; employer feedback; vacancy levels in priority occupations (SOC aligned where possible) | Baselines established year 1 (DfE and JCP/ONS data 2025); For targets see sector specific requirements below. | Employer survey; DfE data; provider ILR | Provision in place; baseline(s) set; initial participation and engagement | Increased delivery and participation | Measurable alignment with employer demand; measurable reduction in skills gaps; sustained increases in skills supply
| 4.1.1.5 There are a range of identified needs in T Levels and other 16-18 provision which would support both direct skills development and progression, with specifics highlighted in the various sectors below | H | WBLPF | CoC, other ERBs, TB, CESSG | O1, O2, O4 | Provision developed /expanded | Increased learner take-up; improved employer satisfaction; improved alignment to employer needs | Increased participation and improved progression outcomes | Participation in FE provision; learner progression rates; employer feedback; vacancy rates (SOC aligned where possible); employment and progression rates; employer, learner and provider feedback; provision introduced | Baseline established year 1 (DfES 2025); target to increase learner starts by 10-15% by year 3 | Employer survey; DfE data; provider ILR | Provision in place; baseline(s) set; initial participation and engagement | Increased delivery and participation | Measurable alignment with employer demand; measurable reduction in skills gaps; sustained increases in skills supply
| 4.1.1.6 Develop an overarching NEET strategy for Cumbria, drawing on learning from other places | H | CCA | CoC, other ERBs, TB, CESSG | O5 | Strategy developed and agreed | Coordinated interventions implemented | Reduction in NEET levels | Participation numbers; employment and progression; NEET numbers and participation rates; initiatives implemented | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | DWP/ONS data; programme monitoring data | Strategy in place | Actions implemented | Reduction in NEET levels
| 4.1.1.7 Undertake a review of professional services (such as accountancy) within practice and industry and determine appropriate actions | M | CoC | Other ERBs, WBLPF | O1, O2, O3, O4 | Review undertaken and actions identified | Changes to provision and engagement strategies | Better alignment between provision and labour market demand; reduced vacancy levels in priority occupations | Participation in provision (types to be determined as part of the review); number of curriculum adjustments; employer, provider and learner feedback; vacancy levels in priority occupations S(SOC aligned where possible) | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Employer surveys; programme monitoring data; DfE data; provider ILR | Review completed; baseline set | Implementation of changes | Measurable employment improvements
4.2 Align educaton and training provision to employer needs | 4.2.1.1 To mitigate staff shortages, develop and implement initiative(s)/pilots(s) to recruit trainers/assessors from industry into FE (and schools) either full or part time, including being made available by their employers, as well as contributing through approaches such as mentoring and masterclasses. Actions including building on a Gatsby Industry Associates model | H | TB & CESSG or WBLPF | TB, CESSG, WBLPF, CoC, other ERBs, SL, BAE | O1, O3 | Initiatives/pilots identified and implemented | Initiatives implemented and/or expanded | Better alignment between provision and labour market demand | Vacancy levels in FE; employer engagement; initiatives implemented | Baseline established year 1 (provider information); target to reduce vacancies by 20-25% and increase employer engagement by 15-20% | Programme monitoring data: provider feedback and vacancy levels | Review completed; baseline set | Increased employer engagement; expansion of activity | Measurable improvements in employment; measurable improvements in employer participation
| 4.2.1.2 Further develop and enhance the Work Based Learning Provider Forum and collaborative working by providers, including shared provision/alignment of curriculum offer, etc, especially in niche occupations and higher levels | H | WBLPF | CoC, other ERBs, L&CIOT | O1, O4 | Forum reviewed and way forward agreed; implementation started | Initiatives implemented and/or expanded; changes to provision; alignment of provision | Better alignment between provision and labour market demand | Number of provision adjustments; number of collaborative initiatives implemented by WBLPF; plan developed and implemented by WBLPF | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Programme monitoring data; provider feedback | Review completed; baseline set; implementation started | Further roll out/development of agreed actions | Measurable improvement in alignment of provision; demonstrable collaborative working
| 4.2.1.3 Work with the CTEC and other TECs as established, including to support niche and low volume requirements (e.g. in construction) | M | WBLPF | CTEC, other TECs, CoC, other ERBs, L&CIOT | O1, O2, O4 | Actions agreed and implementation started | Initiatives implemented and/or expanded; changes to provision; alignment of provision | Better alignment between provision and labour market demand | Number of provision adjustments; number of collaborative initiatives implemented; curriculum changes; number of employers engaged | Baseline no current initiatives (provider feedback); target to implement at least 3 collaboration initiatives by year 3 | Provider feedback; employer feedback (surveys); provider data (ILR), DfE data | Relationships established; actions agreed and implementation started; baselines set | Further roll out/development of agreed actions | Measurable improvement in alignment of provision; demonstrable collaborative working
| 4.2.1.4 Undertake a piece of work on how best address inclusivity in provision and progression/progression into employment | M | CoC | WBLPF, other ERBs, W&HB | O5 | Review undertaken and actions identified | Initiatives implemented | Increased participation and progression amongst disadvantaged groups; increased employment progression among disadvantaged groups | Curriculum changes; participation in FE, ASF, Bootcamps and HE provision by people in disadvantaged groups; progression and employment outcomes by people in disadvantaged groups; NNET numbers of progression rates | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Learner feedback; provider feedback; JCP data; programmes monitoring data, provider data | Review completed; baseline set; implementation started | Further roll out/development of actions | Measurable improvement in participation and progression; OFSTED assessment results
| 4.2.1.5 Complete development of a holistic and placed based education and skills model for Cumbria, building on discussions to date and led by the Combined Authority bringing the skills and education agenda together effectively and supporting progression and achievement through pre-school to post-graduate, including contributing to a reduction in NEETs | H | CCA | CSP, WBLPF | O1, O2, O4, O5, O6 | Review undertaken and actions identified | Initiatives implemented | Better alignment between provision and labour market demand; reduction in NEET numbers; increased progression through pre-school to post graduate | Participation in school, FE & HE; enhanced achievement in school, FE and HE; increased progression from pre-school though to HE; provider, employer and learner feedback; employment and progression; NEET numbers and participation rates | Baseline approach not currently in place; target is to establish a holistic approach by year 2 | DfE data; provider data; feedback from schools and FE/HE providers; programme monitoring data; employer survey feedback; JCP data; ONS | Review completed; baseline set; implementation started | Further roll out/development of actions | Measurable improvement in participation and progression; clear alignment between provision and employer demand
| 4.2.1.5 Determine and implement actions to support schools in addressing shortages in TAs, maths, English and technical | M | CC/WFC | CoC, other ERBs, WBLPF, CSP | O1, O2 | Review undertaken and actions identified | Initiatives implemented | Better alignment between provision and labour market demand | Vacancy levels in schools; provider feedback | Baseline established year 1 (schools 2025 data); target to reduce vacancies by 10% by year 3 | Programme monitoring data: provider feedback and vacancy levels | Review completed; baseline set; implementation started | Expansion of activity | Measurable improvements in employment
| 4.2.1.7 Support providers to address emerging needs in areas such as AI, low carbon, etc (see 4.3.1.1) | H | CoC | WBLPF, RAICO, universities, ERBs, CCA, TB, CESSG | O1, O2, O4 | Review undertaken and actions identified | Changes to provision; initiatives implemented | Better alignment between provision and labour market demand | Curriculum changes; employer feedback (satisfaction); provider feedback | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Employer survey; provider feedback; programme monitoring data; stakeholder surveys | Review completed; baseline set; implementation started | Further roll out/development of actions; broader employer engagement; provision adjusted using evidence | Clear alignment between provision and employers needs/demand
4.3 Reduce skills gaps in key occupations | 4.3.1.1 There is a need across all priority sectors to work with providers and employers to understand the opportunities and impact of AI, robotics and cyber security on workforce skills needs and the curriculum offer and agree appropriate actions. | H | CoC | WBLPF, other ERBs, CMA, RAICo, CESSG, TB, CCA, Universities, L&CIOT | O1, O2, O3, O4 | Review undertaken and actions identified | Changes to provision; initiatives implemented | Better alignment between provision and labour market demand | Curriculum changes; employer feedback (satisfaction), provider feedback | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Employer survey; provider feedback; programme monitoring data; stakeholder surveys | Review completed; baseline set; implementation started | Further roll out/development of actions; broader employer engagement; provision adjusted using evidence | Clear alignment between provision and employers needs/demand
| 4.3.1.2 See also Bootcamps/ASF actions above |  | See above | See above | See above | See above | See above | See above | See above | See above | See above | See above | See above | See above
4.4 Improve employer engagement and take-up of skills provision | 4.4.1.1 Review results of recent small pilot on whether TNAs/independent advice help drive take-up and agree further research/actions | H | CoC | WBLPF, other ERBs | O1, O2, O3 | Pilot launched; employers receiving advice | Increased employer understanding; increased provision uptake | Sustained increase in provision participation | Number of employers supported; apprenticeship starts; employer feedback (measured satisfaction score) | Baseline established year 1 (Chamber and provider 2026); target to increase take-up by 5-10% by year 3 | DfE data; provider ILR; employer engagement records | Pilot delivery; baseline set | Scale services | Embedded service with measurable impact
| 4.4.1.2 Undertake a piece of work exploring the lack of take-up across a range of different provision, despite employers saying it is needed, and how this can be addressed | M | UoC | WBLPF, other universities, CoC, other ERBs | O1. O2, O3, O4 | Review undertaken and actions identified | Changes to provision; initiatives implemented | Sustained increase in provision participation | Number of employers engaged; participation in FE, ASF, Bootcamps and HE provision; curriculum changes; employment and progression outcomes; employer, provider and learner feedback | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | DfE data; provider data; employer surveys; provider surveys; programme monitoring data | Review completed; baseline set; actions identified and started | Roll out/ expansion of activity; broader employer engagement | Clear alignment between provision and employers needs/demand; sustained increased in participation; measurable reduction in skills gaps
| 4.4.1.3 Build on or develop appropriate networks to support effective an appropriate skills delivery, support aggregation of demand and inform/participate in delivery of learning programmes | M | CoC | Other ERBs, WBLPF, CCA TB, CESSG, L&CIOT | O1, O2, O3, O4 | Review undertaken and actions identified; network activity enhanced or started | Networks enhanced; initiatives implemented; employers engaged; changes to provision | Sustained increase in provision participation; sustained increase in employer engagement | Number of employers engaged; curriculum changes; employer feedback (satisfaction); number of networks in place and operating effectively | Baseline could all be operating more effectively; target to have an effective network in place for all priority sectors (5 if Advanced Manufacturing and Clean Energy combined) | Employer surveys; provider feedback; network records | Review completed; baselines set; actions identified and started | Networks functioning effectively; broader employer engagement; provision adjusted using evidence | Measurable reduction in skills gaps; clear alignment between provision and employer demand
| 4.4.1.4 Align LSIP activity with and encourage take-up by employers of Jobcentre Plus, Disability Confident and employability pathways - Jobcentre Plus offers established employer support around recruitment and skills provision, particularly at entry and intermediate levels. This includes employer adviser engagement, vacancy brokerage, work experience, SWAPs, pre-employment preparation, in-work support and Access to Work; the Youth Guarantee also provides a coordinated route for young people into training, work experience and employment; the Disability Confident scheme helps employers recruit, retain, and develop disabled people and those with health conditions | H | CoC | Other ERBs, W&HB, Inspira, Councils, CCA, WBLPF, JCP/DWP | O1, O3, O5 | Joint working arrangements in place; employers engaged with JCP support | Increased participation in JCP-supported pathways; improved engagement for disadvantaged groups | Increased employment rates among those with barriers | Participation in JCP programmes; employment and progression; number of employers engaged | Baseline established year 1 (JCP data 2025); increase employer engagement in these initiatives by 15-20% by year 3 | DfE data; provider ILR; employer engagement records | Alignment established | Increased referrals and participation | Improved employment outcomes
Sector: Advanced Manufacturing (including Defence) (SIC 2562)
4.1 Increase workforce supply in priority sectors | 4.1.1.1 Grow apprenticeship volumes, particular focus on welding, machinists and electrical (SOC5213; SOC5223; SOC2123) | H | COC | SHC, Gen2 | O1, O2, O3 | Increased and more effective learner and employer engagement. See also 4.1.1.1 above | Increased employer use of apprenticeships; increased learner take-up | Reduction in vacancy rates in priority occupations | Apprenticeship starts and completions by level/sector; number of employers engaged; vacancy levels (SOC-aligned where possible) | Baseline established year 1 (DfE data 2025); target +15-20% apprenticeship starts by year 3 | DfE data; provider ILR; employer engagement records | Baselines set; increased participation and engagement | Increased uptake and employer engagement | Sustained increases in skills supply; measurable reduction in skills gaps
| 4.1.1.4 Develop FT undergraduate and PG HE offers in mechanical (SOC2122) and electrical engineering (SOC2123), this will include researching support among employers for undergraduate programmes up to Level 8+ and 18+ year olds to undertake undergraduate studies in Cumbria in STEM subjects; also building on L8 doctoral STAND-Up programme training next generation of nuclear engineers being delivered in part by UoC in Barrow | H | UoC | COC, BAE, SL, CMA, SHC, Gen2, L&CIOT | O1,O2, O6 | Research completed; provision developed/expanded | Increased learner take-up; improved employer satisfaction; improved alignment to employer needs | Better alignment between provision and labour market demand; reduced vacancy levels in priority occupations (SOC aligned where possible) | Participation in HE provision; graduate and young people employment numbers; employer feedback; vacancy rates (SOC aligned where possible) | Baseline established year 1 (provider 2025 data); target at least 1 mechanical and 1 electrical engineering undergraduate course to be added and 1 postgraduate by year 3 | Employer survey; DfE data; provider ILR | Provision in place; baseline(s) set; initial participation and engagement | Increased delivery and participation | Measurable alignment with employer demand; measurable reduction in skills gaps; sustained increases in skills supply
| 4.1.1.3 Grow Bootcamps to meet skills needs at L2 (production operatives etc). (SOC2125) | H | CCA | COC, SHC, Gen2 | O1,O2,O4, O5 | Provision developed/ expanded | Increased learner take-up; improved employer satisfaction | Better alignment between provision and labour market demand | Participation in Bootcamps/ASF; employer satisfaction; employment and progression | Baseline established year 1 Bootcamp 2025 data); target to increase L2 production operative take-up by 10% by year 3 | Employer surveys; programme monitoring data | Provision in place; baseline(s) set; initial participation and engagement | Increased delivery and participation | Measurable alignment with employer demand; measurable reduction in skills gaps; sustained increases in skills supply
| 4.1.1.4 Explore ways to brigade employer demand at L4+, avoid overlapping provider offer to create viable cohorts | M | CoC | SHC, Gen2, L&CIOT | O1, O2, O4 | Provision mapping undertaken and issues and actions agreed | Increased learner take-up; improved employer satisfaction; provision change (new or adapted provision) | Better alignment between provision and labour market demand; reduced vacancy levels in priority occupations; curriculum changes | Participation in Level 4+ provision; employer satisfaction feedback; provider feedback | Baseline established year 1 (provider information); target to achieve employers reporting sufficient provision with at least 1 additional viable Level 4+ provision in place by year 3 | Employer survey; DfE data; provider ILR | Provision mapping completed; issues and actions agreed; baselines established | Implementation of changes/ actions | Measurable alignment with employer demand; measurable reduction in skills gaps; sustained increases in skills supply
4.2 Align educaton and training provision to employer needs | 4.2.2.1 Explore routes to aggregate SME training demand in areas such as Carlisle (vast majority of provision is in West Cumbria/Furness) | M | CoC | CMA, CA, WBLPF, FC, Gen2 | O1, O2, O4 | Review undertaken and actions agreed | Increased learner take-up; improved employer satisfaction; provision change (new or adapted provision) | Better alignment between provision and labour market demand; reduced vacancy levels in priority occupations (SOC aligned where possible) | Numbers of employers engaged; participation in provision; employer satisfaction; provider feedback; aggregation opportunities identified and implemented | Baseline established year 1 (provider and employer survey); target to achieve employers reporting sufficient provision with at least 1 piece of provision to be aggregated by year 3 | Employer survey; DfE data; provider ILR | Provision mapping completed; issues and actions agreed; baselines established | Implementation of changes/ actions | Measurable alignment with employer demand; measurable reduction in skills gaps; sustained increases in skills supply
| 4.2.1.2 Providers to work collaboratively on shared provision/aligned curriculum offers, especially in niche occupations and higher levels | M | CoC | SHC, WBLPF, Gen2, L&CIOT | O1, O2, O4 | Collaboration opportunities identified and actions agreed | Initiatives implemented and/or expanded; changes to provision; alignment of provision | Better alignment between provision and labour market demand | Number of provision adjustments; number of collaborative initiatives implemented; provider feedback; curriculum change reflecting employer needs | Baseline established year 1 (provider and employer survey); target to achieve employers reporting sufficient provision and at least 1 provision collaboration in place by year 3 | Provider feedback; employer feedback (surveys); provider data (ILR), DfE data | Opportunities identified and actions agreed; baseline established | Implementation of changes/ actions | Measurable alignment with employer demand; measurable reduction in skills gaps; sustained increases in skills supply
4.4 Improve employer engagement and take-up of skills provision | 4.4.2.1 Use Sellafield funding to overtrain number of apprentices for SMEs in the supply chain. Pilot service to match those not getting jobs at Sellafield with other employers in West Cumbria | H | SL | CESSG, BECBC, CMA | O1, O2 | Programme/ pilot agreed and implemented | Programme expanded; | Reduction in vacancy rates in priority occupations | Apprenticeship starts and completions by level/sector; number of employers engaged; vacancy levels (SOC-aligned where possible); employer satisfaction | Baseline established year 1 (DfE 2025 data); target to increase relevant apprenticeships by 5-10% by year 3 | DfE data; provider ILR; employer engagement records; employer feedback | Programme/pilot agreed and implemented; baseline established; initial participation and engagement | Increased delivery and participation; broader employer engagement | Sustained increases in skills supply; measurable reduction in skills gaps
| 4.4.2.2 Explore expansion of the University of Cumbria/BAE full-time undergraduate programme being developed in Barrow across the whole of Cumbria, supported by employer and academic provider partners | H | UoC | CoC, employers, WBLPF. Other HE providers, other ERBs | O1, O2, O3, O4 | Review undertaken and way forward agreed | Increased learner take-up; improved employer satisfaction; improved alignment to employer needs | Better alignment between provision and labour market demand; reduced vacancy levels in priority occupations (SOC aligned where possible) | Participation in HE provision; graduate and young people employment numbers; employer feedback; vacancy rates (SOC aligned where possible); employer satisfaction; programme expansion | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Employer survey; DfE data; provider ILR | Review undertaken and way forward agreed; baseline established | Increased delivery and participation; broader employer engagement; provision adjusted using evidence | Measurable alignment with employer demand; measurable reduction in skills gaps; sustained increases in skills supply
Sector: Clean Energy and Net Zero (SIC 2446)
4.1 Increase workforce supply in priority sectors | 4.1.1.1 Grow apprenticeship volumes in plumbing and heating (SOC5315) (West Cumbria and Furness), electrical and mechanical engineering technicians (SOC3133) and ensure new skills needed are incorporated in all relevant apprenticeships | H | CoC | SHC, Gen2, ECITB | O1, O2, O3 | Increased and more effective learner and employer engagement. See also 4.1.1.1 above | Increased employer use of apprenticeships; increased learner take-up | Reduction in vacancy rates in priority occupations | Apprenticeship starts and completions by level/sector; number of employers engaged; vacancy levels (SOC-aligned where possible) | Baseline established year 1 (DfE 2025 data); +15-20% apprenticeship starts by year 3 | DfE data; provider ILR; employer engagement records | Baselines set; increased participation and engagement | Increased uptake and employer engagement | Sustained increases in skills supply; measurable reduction in skills gaps
| 4.1.1.3 Align Skills Bootcamps to skills needs at L2 (production operatives) (SOC5249), and grow ECITB’s Work Ready Pathways programme, develop a comprehensive offer in all parts of Cumbria (supported if possible via ASF) and ensure the new skills needed are incorporated into appropriate short courses | H | COC | EC, ECITB, ZCCP, SHC, Gen2 | O1, O2, O4, O5 | Provision developed/ expanded/ adjusted | Review undertaken and actions identified; programmes launched/expanded; learners enrolled | Changes to provision; improved alignment to learner and employer needs; increased participation of unemployed individuals; improved progression into work or training | Reduced inactivity among local residents; increased participation and progression among unemployed people; participation in ASF/Bootcamps; vacancy levels in priority occupations; NEET numbers and participation rates; curriculum changes; employment and progression; employer, provider and learner feedback | Baseline established year 1 Bootcamps/ASF/ECITB data 2025); target to increase participation by 50% by year 3 | DfE data; provider ILR; employer survey records, Jobcentre Plus data; programme monitoring data | Provision in place; baseline(s) set; initial participation and engagement | Increased delivery and participation | Measurable alignment with employer demand; measurable reduction in skills gaps; sustained increases in skills supply
| 4.1.1.4 Develop FT undergraduate and PG HE offers in mechanical and electrical engineering (SOC3133)- this will include researching support among employers for undergraduate programmes up to Level 8+ and 18+ year olds to undertake undergraduate studies in Cumbria in STEM subjects; also building on L8 doctoral STAND-Up programme training next generation of nuclear engineers being delivered in part by UoC in Barrow | H | UoC | CoC, ECITB, CC, LC, FC, KC, Gen2, L&CIOT | O1, O2, O6 | Provision developed | Increased learner take-up; improved employer satisfaction; improved alignment to employer needs | Better alignment between provision and labour market demand; reduced vacancy levels in priority occupations (SOC aligned where possible) | Participation in HE provision; graduate and young people employment numbers; employer feedback (satisfaction); vacancy rates (SOC aligned where possible); additional provision developed and offered | Baseline established year 1 (provider 2025 data); target at least 1 mechanical and 1 electrical engineering undergraduate course to be added and 1 postgraduate by year 3 | Employer survey; DfE data; provider ILR | Provision in place; baseline(s) set; initial participation and engagement | Increased delivery and participation | Measurable alignment with employer demand; measurable reduction in skills gaps; sustained increases in skills supply
4.2 Align education and training provision to employer needs | 4.2.2.2 Make Cumbrian providers a key part of the supply chain for a fleet of new SMRs, central to new nuclear developments (e.g. Pioneer Park feasibility study). This includes development of pathways for SMR operator and maintenance staff (SOC5221) Levels 3 - 7 | H | CoC | CCA, CC, UoC, LC, Gen2, NCFN, CESSG | O1, O3, O4 | Providers fully engaged with the NSSG and NCfN to support curriculum design for SMR operation and maintenance activities | Changes to provision | Better alignment between provision and labour market demand; reduced vacancy levels in priority occupations (SOC aligned where possible) | Curriculum changes; employer feedback, provider feedback; participation in provision; number of pathways in place | Baseline pathways not in place; target to develop, offer and achieve viable 2 pathways for SMR operator and maintenance staff by year 3 | Employer survey; provider feedback; DfE data; provider ILR | Providers engaged; baselines established; actions agreed | Pathways developed; plans in place for delivery including specialist staff and training/simulation equipment; funding requirements identified | Measurable alignment with employer demand
4.3 Reduce skills gaps in key occupations | 4.3.2.1 Ensure all relevant apprenticeship, study programme, ASF and HE provision in Cumbria incorporates up-to-date learning about net zero (i.e. embed heat pump training within plumbing and heating courses; solar PV within electrical training; net zero regs within project management, etc) | H | CoC | ZCCP, CCA, SHC, WBLPF | O1, O2, O4 | Provision reviewed and initial adjustments identified and implemented | Changes to provision; initiatives implemented | Better alignment between provision and labour market demand | Curriculum changes; employer feedback (satisfaction), provider feedback; | Baseline established year 1 (provider review); target to ensure 100% of relevant provision adapted by year 3 | Employer survey; provider feedback; programme monitoring data; stakeholder surveys | Provision reviewed; initial adjustments identified and implemented; baselines established | Provision further adjusted using evidence | Measurable alignment with employer demand and needs; measurable reduction in skills gaps; sustained increases in skills supply
| 4.3.2.1 Develop a comprehensive short course offer that is accessible to learners in all parts of Cumbria, supported where possible by ASF, new Apprenticeship Units and Skills Bootcamps for the self-employed | H | CoC | SHC, WBLPF, CAL, CCA, ZCCP | O1, O2, O4, O6 | Provision reviewed and developed/ expanded/ adjusted | Review undertaken and actions identified; programmes launched/expanded; learners enrolled | Changes to provision; improved alignment to learner and employer needs | Curriculum changes; employer feedback, provider feedback; participation in FE/ASF/Bootcamps | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Employer survey; provider feedback; programme monitoring data; stakeholder surveys | Initial provision in place; baseline(s) set; initial participation and engagement | Increased delivery and participation; provision further adjusted using evidence | Measurable alignment with employer demand; measurable reduction in skills gaps; sustained increases in skills supply
| 4.3.2.1 Explore evenings and weekend delivery | M | CoC | SHC, WBLPF, CAL | O4 | Review options and decide actions | Changes to provision implemented | Improved alignment to learner and employer needs | Curriculum changes; employer feedback; provider feedback | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Employer survey; provider feedback; programme monitoring data | Provision reviewed; actions identified and implemented; baselines established | Provision further adjusted using evidence | Measurable alignment with employer demand and needs
Sector: Construction (SIC 411, SIC 421, SIC 4299, SIC4312, SIC 4321, SIC 4332, SIC 4554)
4.1 Increase workforce supply in priority sectors | 4.1.1.1 Grow apprenticeship volumes in all trades especially roofing (SOC5314), electrical (SOC5241), groundworkers fenestration (SOC9121) and civil engineering technicians (SOC3114) | H | CoC | SHC, CITB | O1, O2, O3 | Increased and more effective learner and employer engagement. See also 4.1.1.1 above | Increased employer use of apprenticeships; increased learner take-up | Reduction in vacancy rates in priority occupations | Apprenticeship starts and completions by level/sector; number of employers engaged; vacancy levels (SOC-aligned where possible) | Baseline established year 1 (DfE 2025 data); +15-20% apprenticeship starts by year 3 | DfE data; provider ILR; employer engagement records | Baselines set; increased participation and engagement | Increased uptake and employer engagement | Sustained increases in skills supply; measurable reduction in skills gaps
| 4.1.1.3 Align ASF offer to level 2 occupational and upskilling requirements and grow progression to apprenticeships | H | CoC | CAL, CITB, SHC, WBLPF | O1, O2, O4, O5 | Review undertaken and actions identified | Increased learner take-up; improved employer satisfaction | Better alignment between provision and labour market demand | Participation in ASF; employer satisfaction feedback; progression rates; employment and progression rates | Baseline established year 1 ASF data 2025); target to increase L2 take-up by 10% by year 3 | Employer surveys; programme monitoring data | Review completed; baseline set | Implementation of changes | Improved participation and outcomes; Measurable improvement in alignment of provision
| 4.2.1.3 Ensure niche/low volume trades are covered, potentially supported by working with CTEC | M | CoC | CITB, SHC, CTEC | O1, O2, O4 | Actions agreed and implementation started | Initiatives implemented and/or expanded; changes to provision; alignment of provision | Better alignment between provision and labour market demand | Number of provision adjustments; number of collaborative initiatives implemented; employer feedback; provider feedback; curriculum changes | Baseline established year 1 (provider information); target employers reporting appropriate provision available for niche/low volume trades with arrangements for at least 2 niche/low volume trades in place by year 3 | Provider feedback; employer feedback (surveys); provider data (ILR), DfE data | Relationships established; actions agreed and implementation started; baselines set | Further roll out/development of agreed actions | Measurable improvement in alignment of provision; demonstrable collaborative working
| 4.1.1.5 Align 16 to 19 technical education with skills shortages and maximise progression to the sector via apprenticeships | H | CoC | CITB, SHC | O1, O2, O4 | Provision developed /expanded | Changes to provision; alignment of provision | Increased participation and improved progression outcomes; reduction in vacancy rates in priority occupations | Number of provision adjustments; participation in 16-19; employment and progression rates; employer satisfaction feedback | Baseline established year 1 (DfE 2025 data); target to increase progression by 10% by year 3 | Provider feedback; employer feedback (surveys); provider data (ILR), DfE data | Provision in place; baseline(s) set; initial participation and engagement | Increased delivery and participation | Measurable alignment with employer demand; measurable reduction in skills gaps; sustained increases in skills supply
| 4.1.1.5 Explore low learner demand for T Level provision despite strong employer interest and develop/use T level provision to strengthen pathways to occupations at L3+ via apprenticeships and HE | H | CoC | CITB, SHC, CCH | O1, O2, O3, O4 | Review completed (including focus groups in schools); actions identified | Changes to provision | Increased participation and improved progression outcomes | Participation in T Levels; progression via apprenticeships & HE; employer satisfaction; learner feedback | Baseline established year 1 (DfE data); target to increase take-up by 10-15% by year 3 | Provider feedback; employer feedback (surveys); provider data (ILR), DfE data | Review completed; actions identified; baselines established; implementation started | Increased delivery and participation; provision adjusted using evidence | Measurable alignment with employer demand; measurable improvement in participation and progression
4.3 Reduce skills gaps in key occupations | 4.1.1.3 Align ASF offer to Level 2 occupational and upskilling requirements and grow progression to apprenticeships | H | CoC | CAL, CITB, SHC, WBLPF | O1, O2, O4 | Review completed; provision developed /expanded | Increased learner take-up; improved employer satisfaction | Better alignment between provision and labour market demand | Participation in ASF; employer satisfaction feedback; progression rates; curriculum changes | Baseline established year 1 (ASF data 2025); target to increase L2 take-up by 10% by year 3 | Employer surveys; programme monitoring data | Review completed; actions identified; baselines established; initial provision in place | Provision adjusted using evidence; increased delivery and participation | Measurable alignment with employer demand; measurable improvement in participation and progression
| 4.3.2.2 Review existing provision (including CITB) to ensure there is an available programme of short, intensive courses (including Skills Bootcamps) for upskilling for existing workers | H | CoC | CITB, SHC, CC, BTP | O1, O2, O4 | Review completed; provision developed /expanded | Changes to provision; alignment of provision | Increased participation and improved progression outcomes | Employer satisfaction feedback; curriculum changes; | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Employer feedback, DfE data; provider ILR | Review completed; actions identified; baselines established; initial provision in place | Provision adjusted using evidence; increased delivery and participation | Measurable alignment with employer demand; measurable improvement in participation and progression
4.4 Improve employer engagement and take-up of skills provision | 4.4.2.3 Review, strengthen and enforce training and employment requirements (social value clauses) within public procurement in Cumbria | M | COC | CCC, WFC, SHC | O3, O5 | Review completed and actions identified and implemented | Initiatives implemented; increased employer engagement | Sustained increases in participation; employers engaged; increased participation, progression and employment particularly among those with barriers | Apprenticeship starts; number of employer engaged; NEET numbers and participation rates; employment and progression; employer feedback; number of social value clauses strengthened | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Employer surveys; programme monitoring data; DfE data, provider ILR,; provider feedback, JCP data | Review completed; actions identified and implemented; baselines established | Broader employer engagement; increased participation | Measurable improvement in participation and progression
Sector: Visitor Economy (SIC 5510, SIC 5520, SIC 5530, SIC 5590, SIC 5610, SIC 5621, SIC 5629, SIC 5630)
4.1 Increase workforce supply in priority sectors | 4.1.1.1 Pursue growth in relevant apprenticeships, 16-18 and ASF-funded provision to increase the supply of chefs in Cumbria (in demand in other sectors too) and consider amendments to Chartered Manager Degree Apprenticeship to 1 year (Certificate), 2 year (Diploma) and 3 year Degree, building up to a degree with no commitment at the outset (SOC1221, SOC1222) | H | CT | SHC | O1, O2, O3, O4, O6 | Increased and more effective learner and employer engagement. See also 4.1.1.1 above; review and amend CM Degree Apprenticeship | Increased employer use of apprenticeships and other provision; increased learner take-up | Reduction in vacancy rates in priority occupations | Apprenticeship starts and completions by level/sector including chef de partie, commis chef; starts and foundation apprenticeship; completions in other provision; number of employers engaged; vacancy levels (SOC-aligned where possible) | Baseline established year 1 (DfE 2025 data); target +15-20% apprenticeship starts by year 3 | DfE data; provider ILR; employer engagement records | Baselines set; increased participation and engagement, CM Degree Apprenticeship amended | Increased uptake and employer engagement | Sustained increases in skills supply; measurable reduction in skills gaps
| 4.1.1.1 Grow apprenticeships and other provision in other priority occupations (e.g. full-time provision in Travel & Tourism) | H | CT | SHC, PHX | O1, O2 | Increased and more effective learner and employer engagement. See also 4.1.1.1 above | Increased employer use of apprenticeships and other provision; increased learner take-up | Reduction in vacancy rates in priority occupations | Apprenticeship starts and completions by level/sector including hospitality Levels 3-5; starts and completions in other provision; number of employers engaged; vacancy levels (SOC-aligned where possible) | Baseline established year 1 (DfE 2025 data); target +15-20% apprenticeship starts and full-time Travel & Tourism by 5-10% by year 3 | DfE data; provider ILR; employer engagement records | Baselines set; increased participation and engagement | Increased uptake and employer engagement | Sustained increases in skills supply; measurable reduction in skills gaps
| 4.1.1.3 Expand Level 2 ASF and apprenticeship to Level 2 occupational and upskilling requirements such as Hospitality Team Member and Cooks, and use to increase the supply of chefs (SOC5434; SOC5435) | H | CT | SHC, PHX, JCP | O1, O2, O4, O5 | Review completed; provision developed /expanded | Increased employer use of provision; increased learner take-up | Reduction in vacancy rates in priority occupations | Vacancy levels in priority occupations; provision starts and completions; employment and progression outcomes; employer satisfaction feedback | Baseline established year 1 (ASF 2025 data); target to increase L2 take-up by 10% by year 3 | Employer feedback, DfE data; provider ILR, programme monitoring data | Review completed; actions identified; baselines established; initial provision in place | Provision adjusted using evidence; increased delivery and participation | Measurable alignment with employer demand; measurable improvement in participation and progression
4.3 Reduce skills gaps in key occupations | 4.3.2.3 Ensure there are short, intensive programmes available for employee upskilling, focussing on supervisory and people skills (potentially via Skills Bootcamps) (SOC9261) | H | CCA | CT, CoC, SHC, PHX | O1, O2, O4 | Review completed; provision developed /expanded | Increased employer use of provision; increased learner take-up | Increased participation and improved progression outcomes | Employer satisfaction feedback; curriculum changes | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Employer feedback, DfE data; provider ILR | Review completed; actions identified; baselines established; initial provision in place | Provision adjusted using evidence; increased delivery and participation | Measurable alignment with employer demand; measurable improvement in participation and progression
| 4.2.2.3 Further grow catering specialisms in colleges, expanding on existing capability and facilities (SOC9263) | M | CT | SHC, SE | O1, O2, O4 | Review completed; actions identified | Changes to provision; initiatives implemented | Increased participation and improved progression outcomes; reduction in vacancy rates in priority occupations | Employer satisfaction feedback; curriculum changes; vacancy levels (SOC aligned where possible) | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Employer feedback, DfE data; provider ILR | Review completed; actions identified; baselines established; initial provision/facilities in place | Provision adjusted using evidence; increased delivery and participation | Measurable alignment with employer demand; measurable improvement in participation and progression
4.4 Improve employer engagement and take-up of skills provision | 4.4.2.4 Support and build on Tourism Talent Hub to position as one-stop portal for all information on relevant provision and pathways, including short and commercial courses | H | CT | SHC, PHX, WBLPF | O1, O2, O3 | Talent Hub maintained and resources expanded; promotion of Talent Hub | Increased employer use of provision; increased learner take-up | Reduction in vacancy rates in priority occupations | Employer satisfaction; take-up of provision; provider feedback; learner feedback; number of employers engaged | Baseline established year 1 (CT 2025 data); target to increase usage by 10% by year 3 | Employer feedback, DfE data; provider ILR | Maintenance, expansion and promotion of Talent Hub resources; baseline set | Increased engagement with Talent Hub | Improved understanding of opportunities and pathways; improved participation
Sector: Land-Based (SIC 1A10, SIC 0161, SIC 0162, SIC 0120, SIC 0220, SIC 0240, SIC 0311)
4.1 Increase workforce supply in priority sectors | 4.1.1.1 Grow apprenticeships at Levels 2 to 6 in the skills shortage occupations particularly for young people | H | LANSS | KC, MC, UoC, | O1, O2, O4 | Increased and more effective learner and employer engagement. See also 4.1.1.1 above | Increased employer use of apprenticeships; increased learner take-up | Reduction in vacancy rates in priority occupations | Apprenticeship starts and completions by level/sector; number of employers engaged; vacancy levels (SOC-aligned where possible) | Baseline established year 1 (DfE 2025 data); +15-20% apprenticeship starts by year 3 | DfE data; provider ILR; employer engagement records | Baselines set; increased participation and engagement | Increased uptake and employer engagement | Sustained increases in skills supply; measurable reduction in skills gaps
| 4.1.1.1 Explore options to develop pre-apprenticeship activity to enable more young people to progress into apprenticeships | M | LANSS | KC, MC | O1, O2, O4, O5, O6 | Review completed; provision developed /expanded | Provision and pathways developed further; learner participation | Increased participation and progression inro apprenticeships | Pre-apprenticeship starts and completions; apprenticeships starts; curriculum changes | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Provider feedback; employer feedback (surveys); provider data (ILR), DfE data | Review completed; actions identified; baselines established; initial provision in place | Provision adjusted using evidence; increased delivery and participation | Measurable alignment with employer demand; measurable improvement in participation and progression
| 4.1.1.3 Explore options to grow ASF provision to provide pathways for adult learners into the sector | H | LANSS | KC, MC, JCP | O1,O2, O4, O5 | Review completed; provision developed /expanded | Provision and pathways developed further; learner participation | Reduction in vacancy rates in priority occupations; participation in ASF; employment and progression outcomes | Participation in ASF; employer satisfaction; employment and progression; curriculum changes | Baseline established year 1 (ASF 2025 data); target to increase Level 2 take-up by 10% by year 3 | Employer feedback, DfE data; provider ILR, programme monitoring data | Review completed; actions identified; baselines established; initial provision in place | Provision adjusted using evidence; increased delivery and participation | Measurable alignment with employer demand; measurable improvement in participation and progression; sustained increase in skills supply; measurable reduction in skills gaps
| 4.1.1.5 Grow 16-18 provision, particularly T Levels, connecting with apprenticeship pathways to provide pathways to employment | H | LANSS | KC, MC | O1, O2, O4 | Review completed; provision developed /expanded | Provision and pathways developed further; learner participation | Reduction in vacancy rates in priority occupations; participation in ASF; employment and progression outcomes | Curriculum changes; participation in 16-19; employment and progression rates; employer satisfaction feedback | Baseline established year 1 (DfE 2025 data); target to increase participation by 10-15% by year 3 | Increase | Provision reviewed and adjusted | Provision adjusted using evidence; increased delivery and participation | Measurable alignment with employer demand; measurable improvement in participation and progression; measurable reduction in skills gaps
| 4.3.2.4 Ensure training about new technologies and techniques, as well as commercial / financial skills are embedded within curriculum | M | LANSS | KC, MC, ECT | O1, O2, O4 | Provision reviewed and adjusted | Changes to provision; initiatives implemented | Better alignment between provision and labour market demand | Curriculum changes; employer satisfaction feedback, provider feedback | Baseline established year 1 (provider review); target to ensure 100% of relevant provision adapted by year 3 | Employer survey; provider feedback; programme monitoring data; stakeholder surveys | Provision reviewed and adjusted | Provision adjusted using evidence; increased delivery and participation | Measurable alignment with employer demand; measurable improvement in participation and progression; measurable reduction in skills gaps
4.2 Align educaton and training provision to employer needs | 4.2.2.4 Further grow land-based specialisms in providers, expanding on existing capability and facilities, including the alignment of curriculum offers to address any gaps and cohort sizes | M | LANSS | KC, MC, UoC | O1, O2, O4 | Reviews completed; actions identified | Changes to provision; initiatives implemented | Increased participation and improved progression outcomes; reduction in vacancy rates in priority occupations | Employer satisfaction feedback; curriculum changes; vacancy levels; participation in provision; provider feedback | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Employer feedback, DfE data; provider ILR | Review completed; actions identified; baselines established; initial provision in place | Provision adjusted/expanded using evidence; increased delivery and participation | Measurable alignment with employer demand; measurable improvement in participation and progression; sustained increase in skills supply; measurable reduction in skills gaps
| 4.4.2.5 Continue to support and develop LANSS | H | LANSS | CoC, UoC, FN, NFU, CCA, LAs, providers | O1, O2, O3 | LANSS maintained and resources expanded; promotion of LANSS | Increased employer engagement; increased employer use of provision; increased learner take-up | Reduction in vacancy rates in priority occupations | Employer satisfaction feedback; take-up of provision; number of employers engaged feedback; learner feedback; number of providers engaged; website/service users; LANSS continues to operate | Baseline established year 1 (LANSS 2025 data); target for LANSS to continue to operate and to increase usage by 10% by year 3 | Employer feedback, DfE data; provider ILR | Maintenance, expansion and promotion of LANSS resources; baseline set | Increased engagement with LANSS | Improved understanding of opportunities and pathways; improved participation
4.3 Reduce skills gaps in key occupations | 4.3.2.4 Review and support growth of current short course offer within Cumbria (e.g. financial planning/commercial data/digital, new technologies and techniques, along with established driving and animal care courses) | H | LANSS | COC, KC, ECT, MC, UoC | O1, O2, O4 | Review completed; provision developed /expanded | Changes to provision; initiatives implemented | Better alignment between provision and labour market demand | Curriculum changes; employer satisfaction feedback, provider feedback; participation in provision | Baseline established year 1 (provider review); target to ensure 100% of relevant provision adapted by year 3 | Employer feedback, DfE data; provider ILR | Review completed; actions identified; baselines established; initial provision in place | Provision adjusted using evidence; increased delivery and participation | Measurable alignment with employer demand; measurable improvement in participation and progression; sustained increase in skills supply; measurable reduction in skills gaps
Sector: Health & Social Care (SIC 8610, SIC 8620, SIC 8690, 8710, SIC 8720, SIC 8730, SIC 8790, SIC 8810, SIC 8820)
4.1 Increase workforce supply in priority sectors | 4.1.1.1 Grow apprenticeships at Levels 2 to 6 in the skills shortage occupations particularly for young people | H | CoC | SHC, WBLPF | O1, O2, O3 | Increased and more effective learner and employer engagement. See also 4.1.1.1 above | Increased employer use of apprenticeships; increased learner take-up | Reduction in vacancy rates in priority occupations; employment and progression outcomes; better alignment of provision with labour market demand | Apprenticeship starts and completions by level/sector; number of employers engaged; vacancy levels in priority occupations (SOC-aligned where possible) | Baseline established year 1 (DfE 2025 data); target +15-20% apprenticeship starts by year 3 | DfE data; provider ILR; employer engagement records | Baselines set; increased participation and engagement | Increased uptake and employer engagement | Sustained increases in skills supply; measurable reduction in skills gaps
| 4.1.1.3 Align ASF offer to level 2 occupational requirements and improve progression to related work, such as care workers and support workers (SOC6135) | H | CoC | SHC | O1, O2, O4, O5 | Review undertaken and actions identified | Provision and pathways developed further; learner participation | Reduction in vacancy rates in priority occupations; employment and progression outcomes; better alignment of provision with labour market demand | Participation in ASF; employer satisfaction; employment and progression rates; curriculum changes; vacancy levels in priority occupations (SOC aligned where possible) | Baseline established year 1 (ASF 2025 data); target to increase Level 2 take-up by 10% by year 3 | Employer feedback, DfE data; provider ILR, programme monitoring data | Review completed; baseline set | Implementation of changes | Improved participation and outcomes
4.3 Reduce skills gaps in key occupations | 4.3.2.5 Align ASF offer to Level 2 occupational requirements and improve progression to related work, such as care workers and support workers and L2 Adult Social Care Certificate in all areas of the county (SOC6135) | H | CoC | SHC | O1, O2, O4 | Review completed; provision developed /expanded | Provision and pathways developed further; learner participation | Reduction in vacancy rates in priority occupations; employment and progression outcomes; better alignment of provision with labour market demand | Participation in ASF; employer satisfaction feedback; progression rates; curriculum changes | Baseline established year 1 (ASF 2025 data); target to increase Level 2 take-up by 10% by year 3 | Employer feedback, DfE data; provider ILR, programme monitoring data | Review completed; baseline set; | Implementation of changes | Improved participation and outcomes; clear alignment between provision and employer demand; measurable reduction in skills gaps
| 4.3.2.5 Align ASF offer to upskilling needs – digital skills, leadership and management | H | CoC | SHC | O1, O2, O4 | Review undertaken and actions identified | Provision and pathways developed further; learner participation | Increased participation and improved progression outcomes; better alignment of provision with labour market demand | Employer satisfaction feedback; curriculum changes; | Baseline established year 1 (ASF 2025 data); target to ensure all relevant provision introduced /adapted with at least 2 courses added/adapted by year 3 | Employer feedback; programme monitoring data | Review completed; baseline set | Implementation of changes | Measurable reduction in skills gaps; clear alignment between provision and employer demand
4.4 Improve employer engagement and take-up of skills provision | 4.4.2.6 Promote case studies of the effectiveness of values-based recruitment – reliability, compassion, stamina, etc – to improve retention and cut staff turnover | M | Skills for Care | SHC, WBLPF, CoC | O3 | Case studies developed and promoted | Improved recruitment and retention | Reduction in vacancy rates in priority occupations | Employer satisfaction feedback; vacancy levels in priority occupations (SOC aligned where possible) | Baseline established year 1 (provider/S4C 2025 data); target to reduce turnover by 5-10% by year 3 | Employer feedback; | Case studies in place; baseline set; initial engagement | Case studies promoted | Measurable reduction in skills gaps; clear alignment between provision and employer demand
| 4.4.2.7 Undertake review into needs and issues in the sector beyond social care | H | CoC | CSP, WBLPF | O3 | Review completed; actions identified | Changes to provision and engagement strategies | Better alignment between provision and labour market demand; reduced vacancy levels in priority occupations (SOC aligned where possible) | Participation in provision (types to be determined as part of the review); number of curriculum adjustments; learner progression rates; number of employers engaged; provider and employer feedback | Baseline established year 1; target to complete 1 review and agree further target(s) as part of review by year 1 | Employer surveys; programme monitoring data; DfE data; provider ILR | Review completed; actions identified; baseline set; initial participation and engagement | Broader employer engagement; provision adjusted using evidence; delivery and participation | Sustained increases in skills supply; measurable reduction in skills gaps; clear alignment between provision and employer demand
Notes:
- Delivery and monitoring is co-owned by employers and ERBs, FE and HE providers, local authorities and the Combined Authority, Jobcentre Plus and other partners (as listed above)
- As well as playing an active role in planning and implementation, supporting partners (as listed above) will provide data, participate in monitoring and use insights to improve delivery

## Key
Key: Abbreviations
ATA – Apprentice Training Agency | BAE – BAE Systems (Submarines) | BEBC – Britain’s Energy Coast
BTP – Barrow Training Partnership | CA – Carlisle Ambassadors Network | CAL – Cumbria Adult Learning
CCC – Cumberland County Council | CCH – Cumbria Careers Hub | CC – Carlisle College / NCG
CCSG – Cumbria Construction Steering Group | CITB – Construction Industry Training Board | CMG – Cumberland Manufacturing Steering Group
CMA – Cumbria Manufacturing Alliance | DESNZ – Department for Energy Security and Net Zero | DfE – Department for Education
DWP – Department for Work & Pensions | EC – Enterprising Cumbria | ECITB – Engineering Construction Industry Training Board
ECT – Ernest Cook Trust | ERB – Cumbria Chamber of Commerce | FBS – Federation of Small Businesses
FC – Furness College / Blackpool & Fylde College | Gen2 – Gen2 Engineering & Technology Training | JCP – Jobcentre Plus
KC – Kendal College | KS4 – Key Stage 4 (ages 14–16) | KS5 – Key Stage 5 (post-16)
LANSS – Land and Nature Skills Service | LC – Lakes College | LDNP – Lake District National Park
PHX – PHX Training | SHC – Skills Hub Cumbria | SL – Sellafield Ltd / Nuclear Decommissioning Authority
TB – Team Barrow | TEC – Technical Excellence College | UoC – University of Cumbria
WBLPF – Work Based Learners Providers Forum | WFC – Westmorland & Furness Council | ZCCP – Zero Carbon Cumbria Partnership

## Framework Overview
ANNEX B – MONITORING, DELIVERY AND IMPACT FRAMEWORK
This is a live framework and will be reviewed and updated regularly throughout the LSIP period.
PURPOSE
This Annex sets out how LSIP priorities will be delivered and monitored. It provides:
• A clear set of actions to address identified skills needs
• Defined roles and responsibilities across partners
• A consistent approach to tracking progress and impact
• A structured link between:
Skills needs → Actions → Outputs → Outcomes → Impact
All actions contribute directly to the LSIP strategic outcomes (Section 5).
LSIP OUTCOMES
All activity in Annex B aligns to one or more of the following:
O1 Supply of skills aligned to employer demand increases
O2 Skills gaps in the workforce reduce
O3 Employer engagement in the skills system increases
O4 Provision becomes more aligned and responsive (Entry–Level 8)
O5 Participation and inclusion increase (including NEET reduction)
O6 Funding and investment are better targeted
HOW PERFORMANCE IS MEASURED
Performance is monitored using a consistent set of core indicators:
• Apprenticeship starts and completions
• Participation in FE, ASF, Bootcamps and HE
• Employer engagement levels
• Vacancy levels in priority occupations (SOC-aligned where possible)
• NEET participation levels
• Curriculum changes (new or adapted provision)
• Employment and progression outcomes
• Employer, provider and learner feedback
KEY DEFINITIONS (USED THROUGHOUT)
Employer engaged
An employer actively involved in design, delivery, recruitment or training
Participation
Number of learners enrolled in provision
Progression
Movement into employment, further learning or higher-level study
Skills gap reduction
Reduction evidenced through vacancy data and employer feedback
Provision change
New, expanded or adapted curriculum offer
MEASUREMENT APPROACH
Monitoring will be practical and proportionate, drawing on:
• DfE datasets and provider ILR
• Jobcentre Plus and programme data
• Employer and stakeholder surveys
• SIC/SOC classifications where available
DELIVERY TIMESCALES
Year 1 – Establish
Programmes launched, partnerships in place, baselines set
Year 2 – Scale
Participation and employer engagement increase, provision adjusts
Year 3 – Impact
Sustained change with measurable reduction in skills gaps and vacancies
DELIVERY MODEL
Delivery and monitoring are shared across:
• Employers and Employer Representative Bodies (ERBs)
• FE and HE providers
• Local authorities and Combined Authority
• Jobcentre Plus and wider partners
USE OF DATA
Data collected through this framework will be used to:
• Monitor progress against LSIP outcomes
• Support accountability and governance
• Identify gaps, risks and oversupply
• Inform continuous improvement of provision